## Slide 1: CBC Implementation Updates

## Slide 2: Current Operations
Continue Stage I with Region 3B, due to start Stage II startup in September 2019, target a March 2020 go-live
Stage 1 Operational with 2Ingage in Region 2
Stage 1 Operational with Family Tapestry in Bexar County
Rider 21 Report release August 1, 2019

## Slide 3: Region 3B Q3 performance
Region 3b FY 19 Quarter 3 Performance
Performance Measure | Baseline Target (FY16-17 Average) | FY19Q3
Safe in Foster Care | 100% | 99.7%
SSCC Foster Care placements per child | 1.49 | 1.40
% of paid Foster Care days in Family Foster Homes | 75.4% | 80.5%
% of children placed within 50 miles of their home | 74.1% | 75.5%
% cases where all siblings are placed together (on last day of performance period) | 63.0% | 64.3%
% youth turning 18 who have completed PAL Life Skills Training | 90.6% | 100.0%

## Slide 4: Region 1 CBC Update
June 2019, DFPS awarded a CBC contract to Saint Francis Community Services in Texas, Inc.
CBC contract was effective July 1, 2019
6-month start-up period & readiness activities have begun
Anticipate go-live in January 2020
Notes: Joint meetings with regional CPS and Saint Francis leadership have begun, as well as meetings between Saint Francis and the Region 1 provider network. Saint Francis plans to come to October PPP to give an update and overview of their SSCC model.

## Slide 5: Region 8b CBC Update
RFA released on May 2, 2019
RFA closes on August 2, 2019
Evaluation of bids to begin in August
Contract execution anticipated in September-October
Anticipated go-live in April 2020

## Slide 6: Request for Information (RFI)
RFI released on May 30th and closed on June 30th
21 responses received
  Collaboratives/Steering Committees
  Residential Providers
  Community Service Providers
  CASA
  Judiciary
Notes: Received 21 responses. Team hasn’t had time yet to analyze. Once we review/analyze, we will brief our executive leadership. Results of the analysis will inform the updated implementation plan due in December 2019; releasing initial implementation plan in August.

## Slide 7: Data Access & Standards Governance Council
Work continues to establish a two-way data exchange with SSCCs
Switch from IMPACT Legacy to IMPACT R2 Platform completed
Testing two-way data exchange with OCOK underway
  SSCC referral
  Common Application (short form)
  Child placement information
  Child plan
Notes: Additional SSCC IT projects:
SSCC functionality in IMPACT: enhancements to support CBC stage II
Pre-bill for foster care payments

## Slide 8: Process Evaluation
Regions 3b and 2 site visits completed
Region 8a site visit planned for August
Beginning preparation for Region 1 site visit
Preliminary findings due at end of August 2019
Surveys to local stakeholders
Interviews and focus groups:
  SSCCs
  CPS supervisors and caseworkers
  CPS leadership
  CASA
  Attorneys
  Providers
  Foster Parents
  Youth
  Judges